## Went well
Title | Description | Date | Author | Likes
Hosting | We we very successful on hosting | Aug 7, 2020 at 19:31 PM | John Bozarov | 0
Teamwork | The team work really well together and everyone gave 110% | Aug 7, 2020 at 19:31 PM | Korey Brooks | 0
Mob programming |  | Aug 7, 2020 at 19:32 PM | John Bozarov | 0
effort |  | Aug 7, 2020 at 19:33 PM | Devon Brewster | 0
User storie | We got through 11 user stories. | Aug 7, 2020 at 19:33 PM | Korey Brooks | 0
Front End Looked Nice | We decided on John's Capstone as our base since his was the most complete in the front end. | Aug 7, 2020 at 19:33 PM | Jose Moreno | 0
Presentation | We presented well because we rehearsed for hours. | Aug 7, 2020 at 19:34 PM | Korey Brooks | 0
Open communication | We would always share if we did not like something, and how we could improve. | Aug 7, 2020 at 19:38 PM | Marcelo Arthur Barbosa | 0

## Didn't go well
Title | Description | Date | Author | Likes
merging agreement | First day we had a merging conflict so we had to make merging rules between us to make sure we will not mess the master branch again | Aug 7, 2020 at 19:33 PM | John Bozarov | 0
preparation for TDD and Debugging |  | Aug 7, 2020 at 19:34 PM | Devon Brewster | 0
Using Redux which only 1 member was familiar with |  | Aug 7, 2020 at 19:34 PM | Devon Brewster | 0
Unable to upload image | We weren't able to upload the image in the way that the PO wanted | Aug 7, 2020 at 19:35 PM | Korey Brooks | 0
Deployment | Deployment is complicated and took a long time | Aug 7, 2020 at 19:35 PM | Korey Brooks | 0
Tried to anticipate next story | We were slowed down because we tried to anticipate the user Stories and they were rejected | Aug 7, 2020 at 19:36 PM | Korey Brooks | 0
unit testing for the front end |  | Aug 7, 2020 at 19:37 PM | John Bozarov | 0
Not full understanding the User Story | We didn't fully understand the front end user story and worked for hours to implement an HTML page to learn that the PO wanted to view the finalized version of the feature. | Aug 7, 2020 at 19:38 PM | Korey Brooks | 0
TDD Implemented wit Zero Knowledge of Mocking |  | Aug 7, 2020 at 19:39 PM | Jose Moreno | 0
Coding alone. | Coding alone was the biggest blocker we had. | Aug 7, 2020 at 19:39 PM | Marcelo Arthur Barbosa | 0

## Action items
Title | Description | Date | Author | Likes
Focus on the User Story | Complete only the requirements put there by the PO, and do not anticipate future functionality | Aug 7, 2020 at 20:05 PM | Mark Bennett | 0
Push back on the PO when requirements are added | Make sure the Scrum Master understands the User Stories and their requirements. Add new requirements as new backlog items instead of adding them to current stories. | Aug 7, 2020 at 20:09 PM | Mark Bennett | 0